## Sheet1
Date | Time taken | Activity | Workers Name | Status
30th August | 2 hours | database design and implementation | Michael & Nathan | Completed
30th August | 1 hour | Basic UI skeleton | Patrick | Completed
30th August | 1 hour | Paper Design | Nathaniel | Completed
1st September | 1 hour | Contact Page design | Nathaniel | Needs work
1st september | 1 hour & 30mins | Database Connector Class | Michael | Completed
4th Septemeber | 30mins | Entity Relationship Diagram | Edward | Completed
4th September | 20mins | Excel Spreadsheet | Edward | Completed
4th September | 2 hours | Dummy Data | Nathan | Completed
5th September | 2 hours | Contacts page | Nathaniel | Completed
5th September | 30 mins | Story Board | Edward | Completed
Ongoing | 2 hours | Discussion | All workers | Completed
Ongoing | 30 mins | Documentation | All workers | Completed
6th September | 40 mins | Application map | Edward | Completed
6th september | 1 hour | Progress measurement/ Burndown | Edward
total | 16
Sprint 2
6th Sempember | 30mins | Database Connector Modification | Michael | Completed
7th September | 2 hours | Created Terminal Application | Michael | Completed
7th September | 1 hour 30 mins | Databindings setup | Michael | Completed
9th September | 2 hours | Timetable Work | Michael | Completed
10th September | 1 hour 30 mins | Basic Loading | Michael | Completed
10th September | 30 mins | Modified Site Map | Edward | Completed
10th September | 1 hour 30 mins | Add Instruments Feature | Nathan | Completed
16th September | 1 Hour | Database Class to Check Logins | Michael | Completed
17th September | 1 hour | Use Case Diagram | Edward | Completed
17th September | 30 mins | Gather Resources For Design | Edward | Completed
18th September | 30 mins | Mutli- Threaded Timetable | Michael | Completed
18th September | 2 hours | Contracts/ Instruments Tab | Nathaniel | Completed
19th September | 1 hour | UI Testing | Michael | Completed
19th September | 2 hours | Rework of code | Nathan | Completed
Ongoing | 1 hour 30 mins | Booking Window | Patrick | Completed
Ongoing | 1 hour | Documentation | Edward | Completed
20th September | 1 hour | Burndown Charts | Edward | Completed
total 21 hours