## Sheet1
Date | Time taken | Activity | Workers Name | Status
30th August | 2 hours | database design and implementation | Michael & Nathan | Completed
30th August | 1 hour | Basic UI skeleton | Patrick | Completed
30th August | 1 hour | Paper Design | Nathaniel | Completed
1st September | 1 hour | Contact Page design | Nathaniel | Needs work
1st september | 1 hour & 30mins | Database Connector Class | Michael | Completed
4th Septemeber | 30mins | Entity Relationship Diagram | Edward | Completed
4th September | 20mins | Excel Spreadsheet | Edward | Completed
4th September | 2 hours | Dummy Data | Nathan | Completed
5th September | 2 hours | Contacts page | Nathaniel | Completed
5th September | 30 mins | Story Board | Edward | Completed
Ongoing | 2 hours | Discussion | All workers | Completed
Ongoing | 30 mins | Documentation | All workers | Completed
6th September | 40 mins | Application map | Edward | Completed
Ongoing | 40 mins | Progress measurement/ Burndown | Edward | Completed
Total | 15 hours 40 mins